# Daily Progress Report

| Installation / Location | PS-3 |
| --- | --- |
| Subject | Corrosion Monitoring Activities |
| Contract Number | LC241047A0 |
| Assigned Petromec Representatives | Shuaib Palakkavalappil |
| Date of Issue | 22-08-2025 |

## Activities Summary

We arrived at PS-3 this morning and completed all required safety inductions. We then proceeded with submitting work permit and waiting for the permit to be live, mean while we transferred all retrieval tools to the location, We started the work when the permit at the live status

Work activities commenced today, starting with the retrieval and installation of ER PROBE where reported leaking, after the rectification of the location the work is stopped due to Rough Sea and came back to Halul.

| Time | Activities |
| --- | --- |
| 06:00 to 09:30 | Proceed to dock, board vessel to PS-3 |
| 09:30 to 10:45 | Complete platform safety induction, Submit the work permit, awaiting gas test and permit issue |
| 10:45 to 11:30 | Replace ER probe for one location, work stopped due to Rough Sea |
| 12:00 to 14:00 | Proceed to dock , board vessel to Halul |
| 14:30 to 17:30 | Daily Reporting |

Locations Serviced Summary

| Tag No | Line Description | Work Completed |
| --- | --- | --- |
| 53-XCP-970 | 20-OC-530266-1144 20” Oil Line from MP Separator to V5367 Surge Vessel | Removed & Replaced ER Probe. Replaced all pressure retaining seals and rectified reported leaking |

| Tag No | Line No / Description | Pressure (psi) | A/F Orientation | Scope of Work | Retrieved Coupons ID / Holder Length | Coupon\Probe Appearance | Installed Coupons ID / Weight / Material | Tool Used | Location Access | Remedial Actions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 53-XCP-970 | 20-OC-53026-1144 20” Oil Line from MP Separator to V5367 Surge Vessel | 150psi | 12 o Clock | Remove & Replace ER Probe | 4705-S8-K03005-7-00-01) Installed on 27-05-2019 | ER Probe in bend condition | Installed 19.5” type D ER Probe 22-08-2025 | 37” RBSA Retriever (2500 psi) S/N:14698 | Access Fitting Ok. | None Required |
| Access Fitting Photograph |  |  |  | Retrieved Coupons / Device Photograph |  |  | Installed Coupons / Device Photograph |  |  |  |
| Comments |  |  |  |  |  |  |  |  |  |  |
| Retrieved ER Probe (4705-S8-K03005-7-00-01) in bend condition, installed on 27-05-2019 |  |  |  |  |  |  |  |  |  |  |

## Observations & Recommendations

It was noticed the Retrieved ER Probe (4705-S8-K03005-7-00-01) in bend condition, installed on 27-05-2019

24 Hour Lookahead

The plan for Saturday 23rd August  is to continue with coupon and probe replacements on PS-3C Platform.

Shuaib Palakkavalappil – PETROMECH. – shuaib.p@petromech.com.qa